## Sheet1
Skill Level: 1 (No Knowledge) - 5 (Competent)
| Date Reviewed: 04/25/2019 |  | Completed By: Prajal Shrestha | Version :1.0
NO# | Skill Required | Skill Level ( 1- 5) | Traning Action | Training Objective | Time (hrs) | Training Completion Deadline | Traning for?
1 | PHP Programming | 3 | Follow E-commerce web site PHP tutorial on Youtube | Become more confident in the use of PHP and making shopping cart | 20 | 2019-04-20 | Sandip Maharjan, Prajal Shrestha and Sarita khadayat
2 | Database/ OCI Connect | 3 | Follow Notes and Tutorial online | To link website and the database, store information | 10 | 2019-04-13 | Sarita Khadayat and Prajal Shrestha
3 | Bootstrap | 2 | Follow Bootstrap tutorials on Youtube | To build good design of website and make compatible with any device | 10 | 2019-04-20 | Sandip Maharjan and Prajal Shrestha
4 | Paypal Integration | 1 | Follow Tutorials online | Particular in the building of payment method | 10 | 2019-04-12 | Ankit Manandhar
5 | Front End Design | 3 | Follow w3school link and HTML/CSS Tutorial | To build attractive and user friendly user interaction | 20 | 2019-03-25 | Sandip Maharjan, Arpan Basnet and Prajal Shrestha
6 | Wireframe | 2 | Follow Youtube tutorials | wireframe depicts the page layout or arrangement of the website's content, including interface elements and navigational systems, and how they work together | 15 | 2019-03-18 | Prajal Shrestha
7 | Mindmap | 2 | Follow youtube tutorials | visual tool to help structuring information, help us to better analyze, and generate new ideas. | 5 | 2019-03-10 | Prajal Shrestha
8 | Photoshop | 3 | Practise from Youtube, udemy tutorials | To develop skills in editing and altering photographs for the website | 7 | 2019-03-25 | Prajal Shrestha
9 | Illustrator | 3 | Follow youtube tutorials | Helps in developing logo for our website | 9 | 2019-03-26 | Prajal Shrestha
10 | Chat box plugin | 1 | Follow Youtube tutorials, Visit the web for chat box | Helps in communicate with the customer and Trader | 15 | 2019-04-19 | Ankit Manandhar
11 | Content Writing | 3 | Read the article and search the web for blog, post | To keep the website Up to date | 15 | 2019-04-27 | Arpan Basnet and Ankit Manandhar
12 | Search engine Optimization | 1 | Follow Stack overflow, Youtube tutorials | Helps the user to search for the required Items of the product needed | 20 | 2019-04-26 | Ankit Manandhar
13 | EERD/ERD/UML/Conceptual Design | 3 | Follow Study Courses | Helps to build a Database for a website, how it works | 10 | 2019-02-17 | Sarita Khadayat and Prajal Shrestha
14 | MS Project | 2 | Follow Study Courses, Online Tutorials, Recordings | To manage time and to note work progress of a project | 10 | 2019-03-06 | Arpan Basnet
15 | Goole Slides | 4 | Follow tutorials online | To make professional Presentation | 3 | 2019-04-24 | Prajal Shrestha
16 | Microsoft Powerpoint | 4 | Follow tutorials online | To make professional Presentation | 5 | 2019-04-24 | Arpan Basnet